## RoC
RECORDS OF CHANGES
# | Date | In Charge | Change Notes
1
2
3
4
5
6
7

## Product
ONLINE LEARNING PRODUCT BACKLOG
# | Function/Screen | Feature | Level* | Function/Screen Details | Planned
0 | Home Page | Common | Medium | Show sliders + the right sider with the course search box & five featured courses (thumbnail, title) - Slider information: image, title; the user is redirected to the slider's backlink on his/her clicking - Course information: thumbnail, title, list price, sale price; the user is redirected to the Goods Details page on his/her clicking | Iteration 1
1 | User Login | Common | Simple | A pop-up will appear allowing the user to enter the email and password to log in, in the pop-up window there is also a link for the user to reset the password. The system will verify whether the email and password are valid or not. | Iteration 1
2 | User Register | Common | Simple | A popup appears allowing users to enter email, password, full name to register a new account. The user will then receive a code to confirm email account. | Iteration 1
3 | Reset Password | Common | Medium | After clicking on the reset password link in the login pop-up, there will be a reset password pop-up instead of the login popup. In this popup there is an email input box then the system will send a new password to the user's email. | Iteration 1
4 | User Authorization | Common | Complex | This is authorization mechanism in the system, including the specify the user's role, his/her authorized page links (building the displayed menu items and preventing unauthorized access via enter the links directly). The scope of this function also includes building the header, footer, the main function menu (for both Admin and NonAdmin parts) | Iteration 1
5 | User Profile | Common | Simple | This is a pop-up screen which allows the user to edit his/her profile information, including the registered user information and the avatar image (the email is not allowed to change) | Iteration 1
6 | Change Password | Common | Simple | This is a pop-up screen which allows the user to change his/her password by inputting his current password as well as new password (twice) | Iteration 1
7 | Blogs List | Public | Medium | Show the posts paginatedly (sorted by updated date) + the right sider with the post search box, post categories; Post information includes its thumbnail, title, category, post date, brief-info; the user is redirected to the Blog Details page on his/her clicking on a post, redirected to this Blogs List page if the user clicks on a post category. | Iteration 1
8 | Blog Details | Public | Simple | Show post details (including title, author, updated date, brief info, and post content) + the right sider with the post search box, post categories. The Blogs List page is shown when the user clicks on a post category. | Iteration 1
9 | Posts List | Marketing | Medium | Show the paginated list of posts (include posts' id, thumbnail, title, category, author, featured, and status information): - The user can filter the post by category, author, status; also the user can search the post by title - The list can be sortable by title, category, author, featured, or status - The page also have the button/link that allows the user to add new or choose to view/update/show/hide an existing post | Iteration 1
10 | Post Details | Marketing | Medium | Show detailed post information (thumbnail, category, title, brief information, content, flag to turn the featurning on/off, status), from that allow the user to input new post information, view or edit existing post information | Iteration 1
11 | Sliders List | Marketing | Medium | Show the paginated list of sliders (including sliders' id, title, image, status) - The user can filter the sliders by the status + search by title - For each slider, the user can choose to hide, show, edit, delete it | Iteration 2
12 | Slider Details | Marketing | Simple | Show detailed slider information (image, title, status, content) | Iteration 2
13 | Users List | Admin | Simple | Show the paginated list of registered users (include users' id, full name, user title, email, mobile, role, status): - The admin can filter the users by role, status - Allow the admin to seach users by full name, email, mobile - The list can be sortable by id, fullname, gender, email, mobile, role, status - From this page, the admin can choose to add new user, view or edit existing one | Iteration 4
14 | User Details | Admin | Simple | Show detailed user information (registered information+ avatar + role + status), from that allow the user to add new, view or edit the user information; After adding, new generated login password would be email to the new user. | Iteration 4
16 | Lesson View | Customer | Complex | allow customer to access the course lessons for his/her studying | Iteration 2
17 | Quiz Lesson | Customer | Medium | This allows the user to take the topic quiz or view the quiz results | Iteration 2
18 | Quiz Handle | Learning | Complex | This screen allows the user to browse and answer the quiz questions | Iteration 2
19 | Quiz Review | Learning | Complex | This screen allows the user to review the details of the quiz that s/he has just taken | Iteration 2
20 | Dashboard | Marketing | Complex | Show statistics of new subjects (new, all), new registrations (success, cancelled, submitted), revenues (total, by subject categories), customers (newly registered, newly bought), and the trend of order counts (success, all) by day for the last 7 days (the start date & end date can be adjustable) | Iteration 3
21 | Course List | Public | Medium | List available courses based on classification. Each course is displayed in a card containing basic information about the course such as price, short description, thumbmail. If you are a customer, an additional set of courses will be displayed, grouped in a group 'My Courses' containing the courses the customer has signed up for. | Iteration 3
22 | Course Details | Public | Medium | Show details of the value the course will bring. Basic information includes course name, course price, detailed description, skills offered, course objectives, course author, (possibly with a short video introducing the course). | Iteration 3
21 | Subjects List | Course Content | Medium | Show the list of course paginatedly. The shown information for each subject include the id, name, category, number of lessons, owner, and status The user can: - Filter the list by course category & status - Search the course by the name - Choose to add new course (redirect the user to the New Subject page for that) - Edit course information (linked to the Subject Details for that) | Iteration 4
22 | New Subject | Course Content | Medium | The screen is shown with below information for the user to input new course information: name, thumbnail image, category, featured flag, owner, status, and description | Iteration 4
23 | Subject Details | Course Content | Complex | This page allows the admin and the assigned expert to access and prepare the subject information, including the course general information, the dimension, and price package. Only the admin can change the status to Published or Unpublished + add/edit the price packages | Iteration 3
24 | Subject Dimension | Course Content | Simple | This page allow the admin/expert to input or edit subject dimension information, including the following detailed information: type, name, description | Iteration 2
25 | Price Package | Course Content | Simple | This page allows the admin to input or edit subject dimension information, including the following detailed information: name, access duration (in months), status (read-only), list price, sale price, description. The expert can only view the information. | Iteration 3
26 | Subject Lessons | Course Content | Medium | This page shows the list of lessons for a selected package. On this page, the admin/expert is allowed to activate/deactivate, or call the Lesson Details for adding new or editing existing lesson | Iteration 4
27 | Lesson Details | Course Content | Medium | This page allows the admin/expert to input/edit the lesson information | Iteration 4
28 | Questions List | Test Content | Medium | The existing questions list for a specific subject/course are shown here (paginatedly). On this screen, the admin/expert is allowed to filter the questions by the subject, lesson, dimension(s), level, status + search the questions by content Below information are shown for each quesiton in the list: id, content, subject /dimension /lesson, level, status + options to show, hide, edit it; The page also allows the user to import the question (redirect him/her to the Questions Import pop-up screen. | Iteration 3
29 | Question Details | Test Content | Complex | This page allows the admin/expert to input or edit questions information, including following information: subject, dimension(s), lesson, status, content, media (image, audio, video – with preview option), answer options (with the key marked + ability to add, edit, delete), and explanation | Iteration 3
30 | Question Import | Test Content | Medium | This is a pop-up screen which allows user to choose import file and then import the questions in the file into the questions bank. The screen also provides the option for the user to download the sample import template. | Iteration 3
31 | Quizzes List | Test Content | Medium | The existing quizzes are showned in this page paginatedly: - The user can filter the list by subject, quiz types + search quizzes by the name - Each quiz includes following information: id, name, subject, level, # question, duration, pass rate, and the quiz type. From this page, the user has the options to call to the Quiz Details page for adding new or editing existing quiz + delete the quiz. Please note that the quiz can be editted only when there is not any test taken yet. | Iteration 3
32 | Quiz Details | Test Content | Medium | This page allows the user to input or edit quiz information | Iteration 3
33 | Registrations List | Sale | Medium | Show the list of users' registrations - Each registration includes below information: id, email, registration time, subject, package, total cost, status, valid from, valid to, last updated by; - The user can filter the list by subject (searchable), registration time (from, to), status + can search by the email - The list can be sorted by id, email, registration time, subject, package, total cost, status, valid from, valid to - From the list, the user can choose to add new or edit an existing registration via the Registration Details screen as below | Iteration 4
34 | Registration Details | Sale | Medium | Show detailed registration information (subject, package with list price/sale price, full name, gender, email, mobile), registration time, sale, status, valid from, valid to, notes) from that for the user to add new or change the status of a registration with relevant notes (if a registration is created by the user, then s/he can edit other registration information). On changing a registration status to Paid, if the user with relevant registered email does not exist, the system would create one and send back to the user the login information (link, email, pass) along with the other notification notes | Iteration 4
35 | Settings List | Admin | Simple | Show the paginated list of settings (include settings' id, type, value, order, status): - The admin can filter the setting by type, status - Allow the admin to seach settings by value - The list is sortable by id, type, value, order, status - From each setting, the admin can choose to view, activate/deactivate, or edit it - The page also have the button/link that allows the admin to add new setting | Iteration 2
36 | Setting Details | Admin | Simple | Show detailed user information (type, value, order, description, status), from that allow the user to add new, view or edit setting information | Iteration 2

## Iteration 1
THE APPLICATION DEVELOPMENT PROJECT TOPIC
ITERATION 1 BACKLOG
# | Function/Screen | Feature | Level* | LOC | In Charge | Status | Notes
1 | User Login | Common | Simple | 60 |  | Pending
2 | User Register | Common | Simple | 60 |  | Pending
3 | User Authorization | Common | Complex | 240 |  | Pending
4 | Blogs List | Public | Medium | 120 |  | Pending
5 | Blog Details | Public | Simple | 60 |  | Pending
6 | Posts List | Marketing | Medium | 120 |  | Pending
7 | Post Details | Marketing | Medium | 120 |  | Pending

## Iteration 2
THE APPLICATION DEVELOPMENT PROJECT TOPIC
ITERATION 2 BACKLOG
# | Function/Screen | Feature | Level* | LOC | In Charge | Status | Notes
1 | User Login | Common | Simple | 60 |  | Pending
2 | User Register | Common | Simple | 60 |  | Pending
3 | User Authorization | Common | Complex | 240 |  | Pending
4 | Blogs List | Public | Medium | 120 |  | Pending
5 | Blog Details | Public | Simple | 60 |  | Pending
6 | Posts List | Marketing | Medium | 120 |  | Pending
7 | Post Details | Marketing | Medium | 120 |  | Pending

## Iteration 3
THE APPLICATION DEVELOPMENT PROJECT TOPIC
ITERATION 3 BACKLOG
# | Function/Screen | Feature | Level* | LOC | In Charge | Status | Notes
1 | User Login | Common | Simple | 60 |  | Pending
2 | User Register | Common | Simple | 60 |  | Pending
3 | User Authorization | Common | Complex | 240 |  | Pending
4 | Blogs List | Public | Medium | 120 |  | Pending
5 | Blog Details | Public | Simple | 60 |  | Pending
6 | Posts List | Marketing | Medium | 120 |  | Pending
7 | Post Details | Marketing | Medium | 120 |  | Pending

## Iteration 4
THE APPLICATION DEVELOPMENT PROJECT TOPIC
ITERATION 4 BACKLOG
# | Function/Screen | Feature | Level* | LOC | In Charge | Status | Notes
1 | User Login | Common | Simple | 60 |  | Pending
2 | User Register | Common | Simple | 60 |  | Pending
3 | User Authorization | Common | Complex | 240 |  | Pending
4 | Blogs List | Public | Medium | 120 |  | Pending
5 | Blog Details | Public | Simple | 60 |  | Pending
6 | Posts List | Marketing | Medium | 120 |  | Pending
7 | Post Details | Marketing | Medium | 120 |  | Pending