## Wx
PROJECT REPORT
Group | 4
Week | 9/5/2022-13/5/2022
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Project Schedule | Completed
2 | SRS | In Progress
3 | Project Backlog | Completed
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Web Skeleton | TaiVT, ChungLH
2 | Project Backlog | NamHK, TaiVT
3 | SRS | All member
4 | Project Schedule | All member
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | Misleading some parts of SRS | In Progress
2 | Poor Communication | Completed
3 | Not fully grasp how to use github | Pending
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Prepare code designs (packages, classes, attributes & methods) | 2022-05-18
2 | Study coding conventions & practices (from Oracle) | 2022-05-19
3 | Start iteration 1 | 2022-05-18
4 | Team members teach each other how to use github | 2022-05-22
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
Note on C5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C18: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue